## 12-Week (Q1) DevOps Project Pla
Week | Task / Deliverable | Description | Estimated Time (hours) | Difficulty
CW01 | Project Setup | Create GitHub repo, define scope | 6 | Low
CW02 | Docker Setup | Write Dockerfile and build image | 10 | Medium
CW03 | Docker Compose | Run multi-container app locally | 8 | Medium
CW04 | Kubernetes Basics | Install cluster and kubectl setup | 12 | High
CW05 | K8s Deployment | Deploy app using Deployment + Service | 14 | High
CW06 | Helm Charts | Package application with Helm | 10 | Medium
CW07 | CI Pipeline | GitHub Actions build pipeline | 12 | High
CW08 | CD Pipeline | Automated deployment to Kubernetes | 14 | High
CW09 | Terraform Basics | Write Terraform scripts | 10 | Medium
CW10 | Azure Infra | Provision Azure resources | 14 | High
CW11 | Monitoring | Add logging and monitoring | 8 | Medium
CW12 | Documentation | Finalize README and documentation | 6 | Low
Yearly Goal
Complete a cloud-native DevOps project with Docker, Kubernetes, CI/CD, and Terraform on Azure
Quarter | Goal
Q1 | Complete 12-week implementation (Docker, Kubernetes, CI/CD, Terraform)
Q2 | Improve scalability and automation
Q3 | Add monitoring, logging, security
Q4 | Optimization and production readiness